## Sheet1
Project | Date | Raised By | Topic | Issue | External/Internal | Action taken By | Status | Resolution
All Prod Servers | 04.12.2024 | Surya Kant Sharma | Upgrade Failure | There is some failure during upgrade in All 4 servers | Internal | Neeraj Mishra | Resolved | DCC Applied on all four server
App04 | 05.12.2024 | Surya Kant Sharma | Failure in data load step | Tsel App04 :There is failure in 'error import-Discrepancies' | Internal | Surya Kant Sharma | Resolved | The feed is now completed post successful execution of the report job
App02 | 06.12.2024 | Pranveer Singh | Failure in data load step | App02 - Import commit failed | Internal | Pranveer Singh | Resolved | increasing undotbs size and nexted the feed
App02 | 06.12.2024 | Surya Kant Sharma | Failure in data load step | Tsel App02 :There is failure again in 'error import-Commit', Tsel App04 :There is failure in 'error import-ETL' | Internal | Neeraj Mishra | Resolved | Appleid action guided by Engg
App04 | 06.12.2024 | Pranveer Singh | Failure in jobs | App04 - Multiple jobs are down | Internal | Pranveer Singh | Resolved | restarted all the jobs after import-commit so that current feed does not stuck
App04 | 07.12.2024 | Pranveer Singh | Tablespace issue | App04 - Feed failed due to tablespace issue | Internal | Pranveer Singh | Resolved | increasing size now and then will next the feed.
App03 | 07.12.2024 | Surya Kant Sharma | Tablespace issue | Tsel App03: There is a table space issue | Internal | Surya Kant Sharma | Resolved | increasing size now and then will next the feed.
App03 | 10.12.2024 | Surya Kant Sharma | Failure in data load step | Tsel App03 :There is failure in 'error import-Commit' | Internal | Surya Kant Sharma | Resolved | Nexted the failed feed in app03 after increased the pga size
Staging 1 | 13.12.2024 | Akshay Sarmah | DB login issue | Login issue coming in stg1, while trying to login to oracle | Internal | Neeraj Mishra | Resolved | rejected the load and trigger the load again.
Staging 1 | 18.12.2024 | Surya Kant Sharma | DB issue | Tsel Stg1 : Admin console is not opening Also not able to login DBA due to ‘ORA-01034 and ORA-27101’ Shared Memory Issue. | Internal | Surya Kant Sharma | Resolved | Neena Resolved the issue
App01 | 18.12.2024 | Pranveer Singh | datasets pushed manually | App01 - 18th Dec inventory and OSS datasets pushed manually | Internal | Pranveer Singh | Resolved | 18th Dec inventory and OSS datasets pushed manually
Staging 1 | 19.12.2024 | Dipti Prasad | DB issue | File are stuck on load due to db issue | Internal | Dipti Prasad | Resolved | need to restart the service as all jobs are in terminated state in stag1 ...subsequently we will need t reject this load
App02 | 21.12.2024 | Dipti Prasad | files taking time to create batch | APP02: Yesterday migrate feed is since stuck on import audit and files are taking more time to create batch. | Internal | Dipti Prasad | Resolved | The feed is failed on error import-audit ,so Rejected this feed and moving other feed from hold.
App03 | 23.12.2024 | Surya Kant Sharma | Failure in data load step | App03: Also there is failure in ‘Error-Import-Audit’ | Internal | Surya Kant Sharma | Resolved | Resolved by Session With Ranjan
Staging 1 | 23.12.2024 | Surya Kant Sharma | Failure in data load step | Tsel Stg1 :There is failure in 'error import-Commit' | Internal | Surya Kant Sharma | Resolved | Resolved by Session With Ranjan
All Prod Servers | 09.01.2025 | Surya Kant Sharma | Failure in data load step in all servers | Tsel Prod all four server : There are Migrate Feed Stuck in Import-Audit | Internal | Pranveer Singh | Resolved | Applied step 1/2/3 on all 4 - flush task only applied to App02 and App03
App04 | 12.01.2025 | Surya Kant Sharma | Failure in data load step | Tsel App04 :There is failure in 'error import-ETL'. | Internal | Surya Kant Sharma | Resolved | Tsel App04 : After "Clear State" and Next the feed
App04 | 12.01.2025 | Surya Kant Sharma | Failure in data load step | Tsel App04 : After "Clear State" and Next the feed it's faile again in 'error import-ETL' | Internal | Surya Kant Sharma | Resolved | After Adding the space. After "Clear State" and Next the feed
App01 | 17.01.2025 | Surya Kant Sharma | Failure in job | Tsel App01 : there is 'JobWorkflowCtrl' in terminated state. | Internal | Chanchal | Resolved | Steps Suggested by Engg. Team:- Step 1: Restart the job 'JobWorkflowCtrl'. Execute 'InvLic_Report_extract'
App01 | 18.01.2025 | Surya Kant Sharma | Failure in data load | Load failed in app01 with 'code 134' | Internal | Mehul | Resolved | listed steps needed to run:- “Reject the current batch. Initiate the data load again.”
App03 | 20.01.2025 | Surya Kant Sharma | Failure in job | Tsel App03 : there is 'JobWorkflowCtrl' in terminated state | Internal | Shibankur | Resolved | Restart the job 'JobWorkflowCtrl'. Step 2: Execute the 'CM_Report_extract' job. Step 3: Execute the 'InvLic_Report_extract' job.
App01 | 21.01.2025 | Surya Kant Sharma | Failure in data load | Load failed in app01 with 'code 134' | Internal | Mehul | Resolved | listed steps were followed:- “Reject the current batch. Initiate the data load again.”
App03 | 23.01.2025 | Sakshi Sharma | Failure in data loading | Tsel App03 : File Failure in "Error-Preprocess" step | Internal | Mehul | Resolved | Provided the 2 files which have errors along with the server.log for further analyses. Then,For the current batch rejected both the files from Error-Preprocess state.
App03 | 27.01.2025 | Surya Kant Sharma | Migrate feed failuer | Tsel App03 :There is failure in 'error import-Commit' | Internal | Sanjit | Resolved | Tablespace has been added to fix
App01 | 28.01.2025 | Sakshi Sharma | data load did not start | Load Did Not start in APP01 | Internal | Neeraj Mishra | Resolved | Key issue has been fixed for Inventory OSS.
App01 | 05.02.2025 | Surya Kant Sharma | Failure in data load | Load failed in app01 with 'code 134' | Internal | Surya Kant Sharma | Resolved | listed steps were followed:- “Reject the current batch. Initiate the data load again.”
All Prod Servers | 09.02.2025 | Surya Kant Sharma | Unable to login Tsel Enveronment | Due to changes in the procces to access tsel Env. | External | Anton Nugroho | Resolved
All Prod Servers | 10.02.2025 | All Team | Unable to login Tsel Enveronment | Due to changes in the procces to access tsel Env. | External | Anton Nugroho | Resolved | Installed the prisma browser and Global Protect to login the tsel
App03 | 15.02.2025 | Neeraj Mishra | 2file failed in OSS load | 2file failed in OSS load in preprocess | Internal | Neeraj Mishra | Resolved | After Reject the Two Files Move the feed ahead
App01 | 15.02.2025 | Sanjit Mondal | Failure in data load | Load failed in app01 with 'code 134' | Internal | Sanjit Moindal | Resolved | listed steps were followed:- “Reject the current batch. Initiate the data load again.”
All Prod Servers | 16.02.2025 | Neeraj Mishra | unable to connect to TSEL GlobalProtect | unable to connect to TSEL GlobalProtect | External | Anton Nugroho | Resolved
App01 | 16.02.2025 | Sanjit Mondal | Failure in data load step | Failed in Import discrepancy | Internal | Sanjit Moindal | Resolved | Next the failed feed (as per Mehul Suggestion)
App03 | 17.02.2025 | Sakshi Sharma | file failure issue occurred | load faliure as File anable to preprocess. | External | Sakshi Sharma | Resolved | Rejected the file for now issue raised to customer.
App03 | 18.02.2025 | Sakshi Sharma | Gui not access | DB server restarted | External | Sanjit Moindal | Resolved | DB server Database was down and it again started. We don’t have any detail why it is rebooted.
App03 | 18.02.2025 | Surya Kant Sharma | file failed in OSS load | 1file failed in OSS load in preprocess | Internal | Neeraj Mishra | Resolved | After Reject the Files Move the feed ahead
App01 | 19.02.2025 | Surya Kant Sharma | Inv Current File Failed | Inv. Current feed failed in ‘Error-Import-Discrepancies’ | Internal | Surya Kant Sharma | Resolved | Next the failed feed (as per Sandeep's Suggestion)
App01 | 20.02.2025 | Surya Kant Sharma | Failure in data load | Load failed in app01 with 'code 134' | Internal | Surya Kant Sharma | Resolved | listed steps were followed:- “Reject the current batch. Initiate the data load again.”
App04 | 22.02.2025 | Surya Kant Sharma | OSS Feed not moving forward | OSS Feed not moving forward due to AutobackData file in failure (Failure in ‘Error-Preproccess’). | Internal | Surya Kant Sharma | Resolved | rejected the file and share file to eng later for analysis.
App01 | 22.02.2025 | Surya Kant Sharma | Failure in data load step | Failed in Import discrepancy | Internal | Surya Kant Sharma | Resolved | Next the failed feed (as per Mehul Suggestion)
App01 | 23.02.2025 | Surya Kant Sharma | Failure in job | there is 'JobWorkflowCtrl' and ‘CM_Report_extract’ in terminated state. | Internal | Rohan Ghosh & Shibankur | Resolved | Restart the job 'JobWorkflowCtrl'. Step 2: Execute the 'CM_Report_extract' job. Step 3: Execute the 'InvLic_Report_extract' job.
App01 | 28.02.2025 | Surya Kant Sharma | There is no load started yet | as we are having issue checked ‘ERI1/log’ no log created for today. | External | Neeraj Mishra | Resolved | As discussed on call, we have rejected the current load. Till the issue fixed only Huawei files will be loading, no ERI files will be loaded.
App02 | 03.03.2025 | Neeraj Mishra | DB02 server not reachable | DB02 server not reachable | External | SML working on it | Resolved | although it resolved by SML . But actual cause not getting.SML working on it
App01 | 03.03.2025 | Surya Kant Sharma | ther is change for today’s load sequence | Because normally inv is loaded first and oss is done after that. but today Inv is in 'Hold' state and oss feed is in 'Import-ETL' | External |  | In Progress | SML working on it. DCC has been created need to be implement.
App01 | 05.03.2025 | Surya Kant Sharma | OSS load not finished | The day before OSS load did not finished yet as still running in ‘Import-Audit’. Today’s ‘Inv Feed’ is in Import Hold and oss is running in Load. | External |  | Resolved | one of the ericson file having issue and did not process causing delay in the load
App01 | 07.03.2025 | Surya Kant Sharma | Failure in job | JobWorkflowCtrl' and ‘CM_Report_extract’ in terminated state. | Internal | Shibankur | Resolved | Restart the job 'JobWorkflowCtrl'. Step 2: Execute the 'CM_Report_extract' job. Step 3: Execute the 'InvLic_Report_extract' job.
App01 | 11.03.2025 | Sakshi Sharma | server /u01 mount is getting full | /u01 Mount size is getting full and currently it has been reached to 97% in APP01. | External |  | Resolved | listed steps were followed:- “Reject the current batch. Initiate the data load again.”
App01 | 11.03.2025 | Sakshi Sharma | failure in 'error import-Commit' | There is failure in 'error import-Commit' due to new software release mapping issue. | External | Sakshi Sharma/Shibankur | Resolved | 1. The error is caused while trying to insert data into ATTRIBUTE_VALUE_MAP table. 2. The table maintains the mapping between Vendor and User value. 3. However per the Vendor Documentation two vendor values are mapping to same User value. This in turn causes the statement to fail. Similar issue occurred in the month of November 27, 2024 due to the above stated issue. Kindly, execute the DCC SMARTCM-6975.
App01 | 11.03.2025 | Sakshi Sharma | APP01 server /u01 mount is getting full | /u01 Mount size is getting full and currently it has been reached to 97% in APP01. | External | Neena Ji | Resolved | We have removed files after Neeraj confirmation
App01 | 12.03.2025 | Sakshi Sharma | There is failure in 'error preprocess' | space is reaching to 90%. | External | Mehul | Resolved | A disk cleanup is required to remove all the stale data (Backup files, old parsed outputs, error files in loader directory etc) before the batch can be resumed
App03 | 12.03.2025 | Sakshi Sharma | There is failure in 'error-import-discrepencies' | The tables created in the cm_report_extract are being used in Import-Discrepancies | External | Mehul | Resolved | check if the cm_report_extract job is completed. If so, kindly next the feed.
App01 | 14.03.2025 | Sakshi Sharma | There is failure in 'error preprocess' | The server logs suggests that there is a disk space constraint due to which these files are not processed | Internal | Shibankur | Resolved | A disk cleanup is required to remove all the stale data (Backup files, old parsed outputs, error files in loader directory etc) before the batch can be resumed
App01 | 17.03.2025 | Sakshi Sharma | There is failure in 'error-import-diff' step | There is failure in error-import-diff' step as migrate feed got stuck here in this step of data loading. | External | Mehul | Resolved | The Import-Diff failed due to IVIEWLIVEPLAN_WORK tablespace being full. Kindly check the free space in the tablespace, if required execute the cleanup via SMARTCM-7075.
App01 | 19.03.2025 | Sakshi Sharma | There is failure in 'Error-Import-BusinessRules ' step | There is failure in 'Error-Import-BusinessRules' step as migrate feed of OSS data got stuck due to incomplete sql execution.
App04 | 19.03.2025 | Sakshi Sharma | JBoss Services were down | There were several jobs in terminated state now we have restarted the JBoss services. | Internal | Sakshi Sharma | Resolved | restarted the JBoss services.
App01 | 21.03.2025 | Sakshi Sharma | Load failed in TSEL APP01 with 'code 134' | Reject the current batch.Cleanup the $OPTDIR/pid folder.Cleanup the $OPTDIR/Interfaces/*/*/*/*/parser/out directories for any residual parsed files.Initiate the data load again. | Internal | Sakshi Sharma | Resolved | listed steps were followed:- “Reject the current batch. Initiate the data load again.”
App03 | 25.03.2025 | Surya Kant Sharma | Import-Commit job is in terminated state | : Import-Commit job is in terminated state. So that’s why 23rd Inv feed stuck in Import commit and also in Import-Hold. As we know that if anything stops during import commit then we need your advice | Internal | Shibankur | Resolved | Please perform the below mentioned steps: 1. Restart the ‘Import-Commit’ job. 2. We can see 24th’s OSS load and Inventory load and 23rd’s OSS are in Import-Hold state. Please reject these three feeds[9803, 9783, 9763] keeping today’s[25-03-2025] OSS and Inventory feed[9843, 9823].
App03 | 26.03.2025 | Surya Kant Sharma | InvLic_Report_extract job is in terminated state | : InvLic_Report_extract job is in terminated state. So that’s why report not created | Internal | Shibankur | Resolved | 1. Restart the ‘JobWorkflowCtrl’ job to make it into ‘Ready’ state. 2. Rerun the ‘InvLic_Report_extract’ job manually.
App01 | 27.03.2025 | Sakshi Sharma | App01: CleanWorkSchema job is in terminated state, |  | Internal | Rohan Ghosh & Shibankur | Resolved | The “CleanWorkSchema” job is scheduled to run once every week, on Saturday, in our environments. Currently in App01 the job is in a terminated state, and on checking we found that it had last executed on 18th January 2025 in App01. Please restart the job in App01 and we would closely monitor whether it successfully executes on the coming Saturday.
App02 | 27.03.2025 | Sakshi Sharma | App02: Provision-Validate job is in terminated state. |  | Internal | Rohan Ghosh | Resolved | For the “Provision-Validate” on App02, on 25th March, there was a slight interruption because of a connection error during the execution of the various Autobak files, at 5.24
Staging 1 | 28.03.2025 | Surya Kant Sharma | TSEL : Staging upgrade to v8 - | In case space is not an issue, then the possibility is that the raw file is not pulled properly and thus malformed. | Internal | ranjan srivastava | Resolved | Dev team suggested the following: - Reject current load. - Do the required clean-up. - Load the new set.
App01 | 29.03.2025 | Sanjit Mondal | Job failed Import-Discrepancies in TSEL App01 | Kindly check if the cm_report_extract job is completed. If so, kindly next the feed. | Internal | Chanchal | Resolved
App03 | 29.03.2025 | Sanjit Mondal | File-load job is terminated in App03 | Kindly Restart the job. | Internal | Chanchal | Resolved
App02 and App03 | 31.03.2025 | Neeraj Mishra | Implementation of XML validator SMARTCM-7120 | We will get it implemented in App02 and App03
Staging 1 | 01.04.2025 | Neeraj Mishra | Staging upgrade to v8 | We have found in the morning multiple job got terminated in stg Env.Post restarting the failed jobs though feed has been moving ahead.
Staging 1 | 02.04.2025 | Surya Kant Sharma | Staging upgrade to v8 -, 2: Feed is in 'Error ImportDiff' | Tsel Stg1 : Feed is in 'Error import-Diff' due to 'countNewTLVer" is not defined'. Because there is only ‘clear state’ option here. | Internal | Mehul | Resolved | Kindly next the feed with no other action.
Staging 1 | 02.04.2025 | Surya Kant Sharma | Staging upgrade to v8 -, 2: Feed is in 'Error ImportDiff' | Tsel Stg1: Unable to open servers in GUI to check the jobs. There is managed connection issue It seems need to start the jboss. In DB there are some active sessions. | Internal | ranjan srivastava | Resolved | Check, in case no active SQL is running then restart the SmartCM service.
App03 | 03.04.2025 | Sakshi Sharma | App03: ‘JobWorkflowCtrl’ job is in terminated state | Tsel App03: ‘JobWorkflowCtrl’ job is in terminated state. Shall we follow the same steps suggested by you of restarting this job and Execute 'InvLic_Report_extract' | Internal | Mehul | Resolved | follow the same steps as suggested earlier.
Staging 1 | 04.04.2025 | Surya Kant Sharma | Staging upgrade to v8 -, 2: 'there are 2 jobs in terminated state' | Since loading is going on after the upgrade, I want to ask whether the 'Provision timer job and Create Batch' jobs which are terminated. Please suggest Can be restarted ? Oss feed is running in Import Commit step no 189. | Internal | Surya Kant Sharma | Resolved | Restarted the Terminated jobs.
App01 | 05.04.2025 | Surya Kant Sharma | Failure in data load | Load failed in app01 with 'code 134' | Internal | Surya Kant Sharma | Resolved | listed steps needed to run:- “Reject the current batch. Initiate the data load again.”
Tsel STG1 | 08.04.2025 | Neeraj Mishra | Staging Upgrade started with V9 version |  | Internal | Neeraj Mishra, Sanjit | Resolved
Tsel STG1 | 9.042 | Sanjit Mondal | Staging has been upgraded with V9 version |  | Internal | Neeraj Mishra, Sanjit | Completed
App01 | 10.04.2025 | Sanjit Mondal | Failure in data load | Load failed in app01 with 'code 134' | Internal | Sanjit Moindal | Resolved | listed steps needed to run:- “Reject the current batch. Initiate the data load again.”
Staging 1 | 12.04.2025 | Sakshi Sharma | oss feed has come in error-import-commit step | oss feed has come in error-import-commit step | Internal | Sakshi Sharma | Resolved | re-initiate the oss feed by 'Next' from Error-Import-Commit.
Staging 1 | 14.04.2025 | Surya Kant Sharma | oss feed has come in error-import-commit step | oss feed has come in error-import-commit step and some jobs were terminated | Internal | Surya Kant Sharma | Resolved | After ready the terminated jobs re-initiate the oss feed by 'Next' from Error-Import-Commit.
App01 | 14.04.2025 | Surya Kant Sharma | Failure in data load | Load failed in app01 with 'code 134' | Internal | Surya Kant Sharma | Resolved | listed steps needed to run:- “Reject the current batch. Initiate the data load again.”
Staging 1 | 15.04.2025 | Surya Kant Sharma | Tsel Stg1: Oss feed is running in ‘Import-Run Jobs’ for more than 3 hour why it is not getting finished. | Tsel Stg1: Oss feed is running in ‘Import-Run Jobs’ for more than 3 hour why it is not getting finished. | Internal | Surya Kant Sharma | Resolved | Please check if the active column of the state is 1/1. If not, kindly Terminate the state and then restart. The steps mentioned have been completed. Now cache Refresh started.
App02 & App03 | 16.04.2025 | Sakshi Sharma | "JobWorkflowCtrl" & "InvLic_Report_extract" got terminated in both servers | "JobWorkflowCtrl" & "InvLic_Report_extract" got terminated in both servers | Internal | Sakshi Sharma | Resolved | rerun both the jobs and executed "InvLic_Report_extract" job. Then these jobs were up and running
App02 & App03 | 16.04.2025 | Sakshi Sharma | oss load is stuck in "Error-Import-Business-Rules" step | oss load is stuck in "Error-Import-Business-Rules" step | Internal | Mehul | Resolved | Did ‘Clear-State’ and move the feed to ‘Next’.
Staging 1 | 16.04.2025 | Sakshi Sharma | Staging having Inv load in error | Staging having Inv load in error | Internal | Mehul | Resolved | Inv Feed has been rejected and fresh Inv load has been triggered again.
App03 | 17.04.2025 | Sakshi Sharma | Migrate feed of OSS failure | Migrate feed of OSS got stuck in “Error-Import-Commit” step. | Internal | Sakshi Sharma | Resolved | move the feed to ‘Next’.
App01 | 21.04.2025 | Surya Kant Sharma | Failure in data load | Load failed in app01 with 'code 134' | Internal | Surya Kant Sharma | Resolved | listed steps needed to run:- “Reject the current batch. Initiate the data load again.”
App03 | 21.04.2025 | Sakshi Sharma | Failure in data loading | Tsel App03 : File Failure in "Error-Preprocess" step | Internal | Surya Kant Sharma | Resolved | Provided the 1 files which have errors for further analyses. Then,For the current batch rejected the file from Error-Preprocess state.
App02 | 22.04.2025 | Sakshi Sharma | "JobWorkflowCtrl" is in terminated state | "JobWorkflowCtrl" is in terminated state | Internal | Sakshi Sharma | Resolved | we did restart the job and then job came back.
App03 | 23.04.2025 | Sakshi Sharma | migrate feed of Inv Load is in "Error-Import-ETL" | migrate feed of Inv Load is in "Error-Import-ETL" | Internal | Mehul | Resolved | We did clear step but feed fail again.
App03 | 25.04.2025 | Surya Kant Sharma | There is a failure in App03 in “Error-Preprocess” step. | There is a failure in App03 in “Error-Preprocess” step. | Internal | Surya Kant Sharma | Resolved | we proceed with the similar steps like we did previously- “For the current batch rejected the file from Error-Preprocess state”
App04 | 25.04.2025 | Sakshi Sharma | Load Failure in APP04 with 'code 134' | Load Failure in APP04 with 'code 134' | Internal | Sakshi Sharma | Resolved | Kindly pull out the pid files from $OPTDIR/pid folder to establish which MO had the issue. Post that follow the same steps as followed in app01 for such failure
App03 | 25.04.2025 | Sakshi Sharma | Tsel App03- "JobWorkflowCtrl" & "InvLic_Report_extract" jobs are in terminated state | Tsel App03- "JobWorkflowCtrl" & "InvLic_Report_extract" jobs are in terminated state | Internal | Neeraj Mishra | Resolved | According To Rohan: We have had a look into the Application logs for the day, please do rerun both the jobs and execute "InvLic_Report_extract" job.
App01 | 27.04.2025 | Sakshi Sharma | Failure in data load | Load failed in app01 with 'code 134' | Internal | Ssakshi Sharma | Resolved | listed steps needed to run:- “Reject the current batch. Initiate the data load again.”
App03 | 29.04.2025 | Surya Kant Sharma | InvLic_Report_extract and JobWorkflowCtrl got terminated | JobWorkflowCtrl" & "InvLic_Report_extract" jobs are in terminated state due to child job failed. | Internal | Surya Kant Sharma | Resolved | So we rerun both the jobs and execute "InvLic_Report_extract" job like we did previously. sending the server.log file to dev.
App01 | 29.04.2025 | Neeraj Mishra | migrate feed failed in app01 'Error-Import-Commit' due to TS issue | migrate feed failed in app01 due to TS issue | Internal | Sanjit Moindal | Resolved | by Sanjit - added more datafile. work tablespace cleaned now 'next' the feed.
App02 | 02.05.2025 | Sakshi Sharma | In App02 "Import-DiscrepancyStatus" job is in terminated state | In App02 "Import-DiscrepancyStatus" job is in terminated state | Internal | Surya Kant Sharma | Resolved | By Mehul's suggestion : Kindly restart the state. There is no need of running the workflow state.
App01 | 07.05.2025 | Sakshi Sharma | "JobWorkflowCtrl" & "InvLic_Report_extract" got terminated in both servers | "JobWorkflowCtrl" & "InvLic_Report_extract" got terminated in both servers | Internal | Sakshi Sharma | Resolved | rerun both the jobs and executed "InvLic_Report_extract" job. Then these jobs were up and running
App02 | 09.05.2025 | Surya Kant Sharma | "JobWorkflowCtrl" is in terminated state | JobWorkflowCtrl is in terminated state | Internal | Surya Kant Sharma | Resolved | we did restart the job and then job came back.
App02 | 15.05.2025 | Sakshi Sharma | "Inv load" has been stuck in "hold" and "Workflow auto-process " job got terminated. | "Inv load" has been stuck in "hold" and "Workflow auto-process " job got terminated. Also "load" job showing in terminated state. | Internal | Mehul | Resolved | The server log suggest that the DB connections in the pool were destroyed due to being invalidated. So when the application tried to get one of the connections from the pool, there was an error which resulted in the Load state to be Terminated.
App02 | 16.05.2025 | Sakshi Sharma | "File-Preprocess" state got terminated due to some files | "File-Preprocess" state got terminated due to some files and "Workflow auto-process " job got terminated. | Internal | Sakshi Sharma | Resolved | Restarted the "File-preprocess" state and it came in ready state and feed moved ahead
App03 | 16.05.2025 | Surya Kant Sharma | InvLic_Report_extract and JobWorkflowCtrl got terminated | JobWorkflowCtrl" & "InvLic_Report_extract" jobs are in terminated state due to child job failed. | Internal | Surya Kant Sharma | Resolved | 1. Restart the ‘JobWorkflowCtrl’ job to make it into ‘Ready’ state. 2. Rerun the ‘InvLic_Report_extract’ job manually.
App03 | 17.05.2025 | Sakshi Sharma | InvLic_Report_extract and JobWorkflowCtrl got terminated | JobWorkflowCtrl" & "InvLic_Report_extract" jobs are in terminated state due to child job failed. | Internal | Sakshi Sharma | Resolved | 1. Restart the ‘JobWorkflowCtrl’ job to make it into ‘Ready’ state. 2. Rerun the ‘InvLic_Report_extract’ job manually.
App02 | 19.05.2025 | Sakshi Sharma | "Import-hold" job got terminated | restarted the job | Internal | Mehul | Resolved
STG1 | 22.05.2025 | Surya Kant Sharma | Managed Connection Issue | We have observed managed connection error in Tsel STG1. So GUI did not open. | Internal | Surya Kant Sharma | Resolved | Post restarting services dataset is now getting processed
App01 | 25.05.2025 | Sakshi Sharma | Network-load got failed | Load failed in app01 with 'code 134' | Internal | Sakshi Sharma | Resolved | listed steps needed to run:- “Reject the current batch. Initiate the data load again.”
App02 | 26.05.2025 | Sakshi Sharma | "Report-generate" job got terminated | "Report-generate" job got terminated and so the workflow auto process. | Internal | Sakshi Sharma | Resolved | Restarted the job and load is moving
App03 | 27.05.2025 | Sakshi Sharma | Auto-workflow Job was terminated in “merge” state | Auto-workflow Job was terminated in “merge” state | Internal | Sakshi Sharma | Resolved | Restarted the job and load is moving
App03 | 28.05.2025 | Anton Nugroho | file failure in "error-pre-process" step | file failure in "error-pre-process" step and the load has been stucked | Internal | Anton Nugroho | Resolved | Rejected the xml failed file and feed moved ahead. File was not available
Staging 1 | 01.06.2025 | Surya Kant Sharma | Managed Connection Issue | We have observed managed connection error in Tsel STG1. So GUI did not open. | Internal | Surya Kant Sharma | Resolved | Post restarting services dataset is now getting processed
Staging 1 | 01.06.2025 | Surya Kant Sharma | oss feed has come in error-import-commit step | oss feed has come in error-import-commit step and one job 'Import-PreCreateMetaData' were in terminate state which one restarted | Internal | Surya Kant Sharma | Resolved | After next the failed feed, it is moving ahead.
App02 | 02.06.2025 | Sakshi Sharma | create-batch job terminated | create-batch job terminated due to “java.net.SocketTimeoutException: Socket read interrupted”. | Internal | Mehul | Resolved | Restarted the job and load is moving. SPS-279 has been raised for the same. R&D Suggest - While we drill down on the exact reasons for these failures please continue to restart the failed jobs/workflow states.
staging | 03.06.2025 | Sakshi Sharma | multiple jobs in terminated state | The error message in the application logs is ”java.io.IOException: Connection reset by peer, Authentication lapse 60009 ms.” | Internal | Mehul/Sanjit | Resolved | Restarted the job and load is moving.As an immediate step please add more space to SYSAUX tablespace and let us observe the system for any logon errors.Sanjit had increased the SYSAUX tablespace and till now no timeout error was noticed in the alert log.
App01 | 08.06.2025 | Sakshi Sharma | OSS load got failed and stuck in “error-import-audit”. | OSS load got failed and stuck in “error-import-audit”. | Internal | Mehul | under investigation | We have “Next” the feed and now the load come out from error. the issue is in under investigation.
Tsel Stg1 | 10.06.2025 | Surya Kant Sharma | ‘Import-Hold’ job were terminated state | ‘Import-Hold’ job were terminated state | Internal | Surya Kant Sharma | Resolved | we restarted it now 7th June Oss data is running in 'Import-ETL'.
Tsel Stg1 | 10.06.2025 | Sanjit Mondal | oss feed has come in error-import-commit step | The issue is again due to “Connection reset by peer” i.e. The Database was not able to service a connection request. Please check if there are still errors coming up in the ALERT log. | Internal | Sanjit Moindal | Resolved | After next the failed feed, it is moving ahead.
Tsel Stg1 | 11.06.2025 | Surya Kant Sharma | Tsel Stg1: We have observed managed connection error | We have observed managed connection error in Tsel STG1. So GUI did not open. | Internal | Surya Kant Sharma | Resolved | Post restarting services one job 'Import-PreCreateMetaData' were in terminate state which one restarted.
Tsel Stg1 | 12.06.2025 | Surya Kant Sharma | One job 'Merge' were in terminate state | One job 'Merge' were in terminate state | Internal | Surya Kant Sharma | Resolved | One job 'Merge' were in terminate state which one restarted and feed moving ahead. Server.log sent to R&D.
Tsel Stg1 | 13.06.2025 | Surya Kant Sharma | Tsel Stg1: We have observed managed connection error | Tsel Stg1: We have observed managed connection error. Three jobs ('SystemMonitor', ‘FilePurge’, ‘TablePurge’) were in terminate state | Internal | Surya Kant Sharma | Resolved | which three restarted manually. 8rth June Oss feed is running in ‘Import-Commit’.
Tsel Stg1 | 13.06.2025 | Surya Kant Sharma | Tsel Stg1: We have observed managed connection error | We have observed managed connection error in Tsel STG1. So GUI did not open properly. Post restarting services there was a feed in ‘Error-Import-Business-Rule’. one job 'Import-PreCreateMetaData' were in terminate state. | Internal | Surya Kant Sharma | Resolved | Post restarting services there was a feed in ‘Error-Import-Business-Rule’ which is moved from the failed feed by next. one job 'Import-PreCreateMetaData' were in terminate state which one restarted.
Tsel STG1 | 13.06.2025 | Surya Kant Sharma | Sub Change : Tsel Stg1:8th June Oss feed failed again in ‘Error-Import-Business Rules’. ( We have observed managed connection error in Tsel STG1) | 8th June Oss feed failed again in ‘Error-Import-Business Rules’. | Internal | Surya Kant Sharma | Resolved | Specialy in this case suggested by Mehul: Kindly perform a “Clear State” action and then Next the feed.
App02 | 15.06.2025 | Surya Kant Sharma | InvLic_Report_extract and JobWorkflowCtrl got terminated | JobWorkflowCtrl" & "InvLic_Report_extract" jobs are in terminated state due to child job failed. | Internal | Surya Kant Sharma | Resolved | 1. Restart the ‘JobWorkflowCtrl’ job to make it into ‘Ready’ state. 2. Rerun the ‘InvLic_Report_extract’ job manually.
App02 | 16.06.2025 | Sakshi Sharma | "createBatch" job in terminated state | APP02- "createBatch" job in terminated state due to JDBC connection error | Internal | Mehul | under investigation | Restarted the "createbatch" job manually. Similer issue on 7th November
App03 | 18.06.2025 | Sakshi Sharma | JobWorkflowCtrl" & "InvLic_Report_extract" jobs are in terminated state | JobWorkflowCtrl" & "InvLic_Report_extract" jobs are in terminated state due to child job failed during runtime exception | Internal | Sakshi Sharma | under investigation | Restarted ‘JobWorkflowCtrl’ & ‘InvLic_Report_extract’ job manually. Then Executed ‘InvLic_Report_extract’ job.
Tsel Stg1 | 25.06.2025 | Sanjit Mondal/Neeraj | OSS feed is running in Import-ETL for more than 10 hours in TSEL STG1 | OSS feed is running in Import-ETL for more than 10 hours in TSEL STG1. The few active sessions are given here | Internal | Surya Kant Sharma | Resolved | The Batch loaded nearly 10 times of the data (453 Million loaded against 49 MM). The reason was incompletion of “Gather Oracle Stats” job which resulted in partitions not created for loader log table and thus caused the loader to load data repeatedly. The current Feed which was in Import-ETL has been rejected and the gather stats job triggered. The dataset will be loaded again post completion of the job. raised to R&D. waiting for respose.
Tsel STG1 | 30.06.2025 | Surya Kant Sharma | Tsel Stg1: We have observed managed connection error | and one job 'Import-PreCreateMetaData' were in terminate state which one restarted | Internal | Surya Kant Sharma | Resolved | Post restarting services one job 'Import-PreCreateMetaData' were in terminate state which one restarted. the issue is in under investigation.
App01 | 30.06.2025 | Sanjit Mondal | JobWorkflowCtrl" & "InvLic_Report_extract" jobs are in terminated state | InvLic_Report_extract job is failed due to ‘unable to extend IVIEWLIVEPLAN_TEMP’ in Tsel app01, it is already allocated 1.4 TB of storage in PLAN_TEMP tablespace but it was fully occupied. | Internal | Sanjit Moindal | Resolved
App02 | 01.07.2025 | Sakshi Sharma | both(OSS & INV) load was stuck and "provision-preactivate" job was terminated | In morning, we encountered both the loads had been stuck. OSS load was stuck in “Merge” and INV load was stuck in “Hold”. Also “Provision-Preactivate” job was terminated, we have Restarted the Job. Post Re-run the job, both the loads start moving. | Internal | Mehul | under investigation
Tsel STG1 | 01.07.2025 | Sanjit Mondal | Import-Run job is running for more than 10 hours in TSEL staging | Import-Run job is running for more than 10 hours in TSEL staging | Internal | Neeraj Mishra | Resolved | restarted the job and it is completed now but it should completed by self.
App01 | 01.07.2025 | Neeraj Mishra | JobWorkflowCtrl" & "InvLic_Report_extract" jobs are in terminated state | Inventory extract failed today again with similar error and OSS migrate feed also failed. | Internal | Neeraj Mishra | under investigation
Tsel STG1 | 04.07.2025 | Surya Kant Sharma | We have observed managed connection error in Tsel STG1 | Tsel Stg1: We have observed managed connection error in Tsel STG1. So GUI did not open properly. Post restarting services there one job 'Import-PreCreateMetaData' were in terminate state which one restarted. | Internal | Surya Kant Sharma | Resolved | Post restarting services one job 'Import-PreCreateMetaData' were in terminate state which one restarted.
Tsel STG1 | 07.07.2025 | Surya Kant Sharma | Tsel Stg1: We have observed managed connection error | We have observed managed connection error in Tsel STG1. So GUI did not open properly. Post restarting services there was a feed in ‘Error-Import-Business-Rule’. one job 'Import-PreCreateMetaData' were in terminate state. | Internal | Surya Kant Sharma | Resolved | Post restarting services there was a feed in ‘Error-Import-Business-Rule’ which is moved from the failed feed by next. one job 'Import-PreCreateMetaData' were in terminate state which one restarted.
App03 | 10.07.2025 | Surya Kant Sharma | JobWorkflowCtrl" & "InvLic_Report_extract" jobs are in terminated state | "JobWorkflowCtrl" & "InvLic_Report_extract" jobs are in terminated state due to child job failed. | Internal | Surya Kant Sharma | Resolved | We have restarted both the jobs and they are in ready state now. And Inv report is yet to be generated so We have executed the “InvLic_Report_extract” job manually.
Tsel STG1 | 01.07.2025 | Sanjit Mondal | Import-Run job is running for more than 10 hours in TSEL staging | Import-Run job is running for more than 10 hours in TSEL staging | Internal | Neeraj Mishra | Resolved | Neeraj has restarted the job and it is completed now but it should completed by self.
App01 | 01.07.2025 | Sanjit Mondal | InvLic_Report_extract job failed | InvLic_Report_extract job is failed due to ‘unable to extend IVIEWLIVEPLAN_TEMP’ in Tsel app01, it is already allocated 1.4 TB of storage in PLAN_TEMP tablespace but it was fully occupied. the below query was consuming huge cache. | Internal | Sanjit Mondal | Resolved | Increase the Table Space
Tsel STG1 | 14.07.2025 | Sakshi Sharma | managed connection error and Gather Stats Issue | Oss feed failed in ‘Error-Import-ETL’.Gather Stats has started on 12-07-2025 but it is not finished yet. | Internal | Mehul | Resolved | The Import-ETL state was Nexted without doing a “Clear Step” action after the service restart. This resulted in one of the step not getting executed (The Count column is blank).As such the subsequent step (Step 680) where the table was required failed with “Table or View does not exists”. Kindly ensure appropriate actions are taken post a service restart. For the current feed please do a “Clear State” and Next the feed.
Tsel STG1 | 16.07.2025 | Surya Kant Sharma/Neeraj | Telkomsel Staging: Request for the Orchestrator deployment | Telkomsel Staging: Request for the Orchestrator deployment | Internal | Surya Kant Sharma/Neeraj | Completed
App04 | 18.07.2025 | Surya Kant Sharma/Sanjit Mondal | TSEL : Production upgrade to v9 -APP04 | TSEL : Production upgrade to v9 -APP04 (No issue) | Internal | Sanjit Mondal | Completed
App04 | 21.07.2025 | Sanjit Mondal | loaded rows for OSS are very less in TSEL App04 | loaded rows for OSS are very less in TSEL App04 | Internal | Sanjit Moindal | Resolved
App04 | 21.07.2025 | Surya Kant Sharma | Base location for reports 'cd $HOMEDIR/Smartcm' not accesed by SML | Base location for reports 'cd $HOMEDIR/Smartcm' not accesed by SML | Internal | Surya/Sanjit | Resolved | As such the subsequent step (Step 680) where the table was required failed with “Table or View does not exists”.
Tsel STG1 | 25.07.2025 | Sakshi Sharma | managed connection issue. OSS Feed was stuck. | Yesterday OSS feed was stuck in “Import-InterDomainMatch” step. Today post restarting the services feed is moving. one job 'Import-PreCreateMetaData' were in terminate state which has been restarted. Now feed is moving ahead. | Internal | Chanchal | Resolved
App03 | 26.07.2025 | Sanjit Mondal | V9 upgrade status | TSEL App03 upgrade has not yet completed. The below statement is running since 15 hours. ~/SmartCM/scripts/installer.sh ~/SmartCM/patch/sql/close_deleted_entities.xml 7026 | Internal | mehul | Resolved | Kindly ensure appropriate actions are taken post a service restart.
App03 | 28.07.2025 | Anton Nugroho | Migrate feed of Inventory failure in “Error-Import-Commit” | Migrate feed of Inventory got stuck in “Error-Import-Commit” step. | Internal | Mehul | Resolved
App01 | 28.07.2025 | Surya Kant Sharma | Due to Managed connection issue-yesterday and today's load didn't initiated. | Due to Managed connection issue last load was on Saturday, Jul 26th, yesterday and today's load didn't initiated, Post restarting service 28th July Oss load started now running in merge. Also 27th july reports not created. | Internal | Chanchal | Resolved | For the current feed please do a “Clear State” and Next the feed.
App04 | 28.07.2025 | Surya Kant Sharma | Load failed in app04 with 'code 134' | Load failed in app04 with 'code 134'. Re initiate the load by putting the OSS data in 'oss-input-main'. But it is not showing in GUI. | Internal | Anton Nugroho | Resolved
App03,04 | 01.08.2025 | Megha Sharma | Group icon not visible in production after V9 Upgrade | After the upgrade, the group icon is not visible on App03 and App04. However, it is still visible on App01, where the upgrade has not yet been applied . Please confirm SMARTCM-7160 needs to be reapplied | Internal | Sanjit Mondal | Resolved | Applied SMARTCM-7160
App02 | 04.08.2025 | Surya Kant Sharma | Is there any change for today’s sequence | App02: Is there any change for today’s sequence ? Because normally inv is loaded first and oss is done after that. but today Inv is in 'Import-Hold' state and oss feed is in 'Import-commit'
Tsel STG1 | 07.08.2025 | Sakshi Sharma | managed connection issue | Today morning we observed managed connection error in Staging1 when OSS feed was loading and it got stuck at “Import-Diff” step, after restarting the Server’s Services the load moved to next step. Also "Import-PreCreateMetaData" job was terminated, we restarted the job. | Internal |  | Resolved
Tsel STG1 | 08.08.2025 | Sakshi Sharma | feed is stuck in "Import-BusinessRules" step | The feed which moved yesterday from “Import-Diff” step is now stuck in "Import-BusinessRules". Are we good to go with “clear state” at this step. | Internal | mehul | Resolved | To proceed further with the feed, kindly do a “Clear State” and next the error feed
Tsel STG1 | 11.08.2025 | Sanjit Mondal | OSS feed moves to Error-Import-BusinessRules in TSEL staging | OSS feed moves to Error-Import-BusinessRules in TSEL staging | Internal | chanchal | Resolved | Did ‘Clear-State’ and move the feed to ‘Next’.
Tsel STG1 | 12.08.2025 | Sanjit Mondal | database FATAL NI/connection issue | In TSEL staging OSS feed is in ‘Import-BusinessRules’ since morning. The job is getting terminated even we restart it. It shows connection error in the log. There is FATAL NI error in the database alert log for last few days. Cannot see any active running session. Oracle autotask job was also not completed. It is better to restart the DB instance | Internal
App02 | 22.08.2025 | Sakshi Sharma | Provision-Activate job is terminated | APP02- Provision-Activate job is terminated due to Ping java program got failed. | Internal | mehul | Resolved | Please restart the state. The log shows error as “java.nio.channels.ClosedChannelException."
App02 | 22.08.2025 | Sakshi Sharma | migrate feed took more time than usual in running in "import-diff" step | migrate feed of OSS is running in “import-diff” step since more than 2 hours today and it did take more than 12 hours yesterday to complete in same step(import-diff) as compared from last row days. | Internal | mehul | Resolved | Seems the queries running on STREAM_ENTITY_ATTRIBUTE are getting slowed down since yesterday. The queries which used to get complete in 5-6 minutes are now taking 2+ hours. From the last 6 days, around 262 Million records are inserted into/deleted from this table. So possibly the statistics have gone stale since the last gather stats. Please plan to gather the statistics on the said table
App03 | 24.08.2025 | Sanjit Mondal | Jboss service was down in TSEL App03 since morning | Jboss service in TSEL App03 was down yesterday for a long time, we had restarted and feed was resumed as described in the trail mail. Now yesterday’s OSS feed is stuck in Import-audit for more than 6 hours. | Internal | Sanjit Mondal | Resolved | Modified JVM parameter to 20 gb as suggested by R&D.
Tsel STG1 | 25.08.2025 | Surya Kant Sharma | Load stuck in Merge due to insufficient space | After initiate the Load on 23.08.2025 it was stuck in merge for a long time and 5 files in ‘File Pre process’. Due to a space crisis, it was necessary to perform a cleanup and reload operation. As part of this process, the parcer/out directory was cleaned up first to free up space. Now need to reject the batch and 5 files in ‘File Pre process’ | Internal |  | Resolved
App03 | 26.08.2025 | Surya Kant Sharma | Tsel App03: Failure in "Error-Preprocess" step | Failure in "Error-Preprocess" step | Internal | Surya | Resolved | There is a failure in App03 in “Error-Preprocess” step. we proceed with the similar steps like we did previously- “For the current batch rejected the file from Error-Preprocess state”.So Rejected the failed file. And file send to R&D for investigation. Modified ftp script to implement error file checkong
App03 | 27.08.2025 | Anton Nugroho | Tsel App03: Failure in "Error-Preprocess" step | Failure in "Error-Preprocess" step | Internal | Anton Nugroho | Resolved | There is a failure in App03 in “Error-Preprocess” step. we proceed with the similar steps like we did previously- “For the current batch rejected the file from Error-Preprocess state”.So Rejected the failed file. And file send to R&D for investigation. Modified ftp script to implement error file checkong
App03 | 28.08.2025 | Anton Nugroho | Tsel App03: Failure in "Error-Preprocess" step | Failure in "Error-Preprocess" step | Internal | Anton Nugroho | Resolved | There is a failure in App03 in “Error-Preprocess” step. we proceed with the similar steps like we did previously- “For the current batch rejected the file from Error-Preprocess state”.So Rejected the failed file. And file send to R&D for investigation. Modified ftp script to implement error file checkong
App01 | 28.08.2025 | Sanjit Mondal | OSS feed in TSEL App01 moved to Error-Import-Discrepancies | OSS feed in TSEL App01 moved to Error-Import-Discrepancies . we faced difficulties to login to the app01 server also. We have ‘Next’ the feed. It seems some network issue as per Server log. It seems there is a connectivity issue between app01 & DB01, tnsping is also not working from client side. Although database is up and I can connect from sql dev. | External | Anton/Sanjit | under investigation | Anton escalated this to both SML and Telkomsel for further investigation.
App03 | 29.08.2025 | Anton Nugroho | Tsel App03: Failure in "Error-Preprocess" step | Failure in "Error-Preprocess" step | Internal | Anton Nugroho | Resolved | There is a failure in App03 in “Error-Preprocess” step. we proceed with the similar steps like we did previously- “For the current batch rejected the file from Error-Preprocess state”.So Rejected the failed file. And file send to R&D for investigation. Modified ftp script to implement error file checkong
Stg2 | 10.09.2025 | Sanjit Mondal | OSS feed in TSEL Staging-2 is getting failed in ‘Import-diff’ | OSS feed in Staging-2 is getting failed in ‘Import-diff’ several times due to insufficient storage in ‘WORK’ tablespace. It also failed when the WORK tablespace allocation was 1.4T and now I have increased it to 1.7T. Iin staging-1 the same tablespace is only 145GB but in staging -2 it is taking huge storage. | Internal | Sanjit Mondal | Resolved | Guided by Sandeep: this is happening due to Huge count of Diff. Since all the files have been dump together in 1 go and this is the 1st run on staging-2 ,the size of diff count is in billions (approx. 1.7 billion records). This is the reason space issue is encountered. So please add more space to handle space issue .
Stg2 | 13.09.2025 | Sanjit Mondal | OSS feed failed in ‘Impor-BusinessRule’ in Tsel Staging-2 | OSS feed failed in ‘Impor-BusinessRule’ in Tsel Staging-2, it shows invalid character error. | Internal |  | under investigation
App03 | 14.09.2025 | Surya Kant Sharma | There was 'JobWorkflowCtrl' in terminated state | There was 'JobWorkflowCtrl' in terminated state During job execution, a java.nio.channels.ClosedChannelException was thrown, indicating that an I/O channel was prematurely closed while an operation was being performed on it. |  | Surya Kant Sharma | Resolved | So followed these following steps. 1. Restart the 'JobWorkflowCtrl' job. 2. Execute the 'CM_Report_extract' job. 3. Execute the 'InvLic_Report_extract' job.
App03 | 15.09.2025 | Sanjit Mondal | file failure in "error-pre-process" step | Failure in "Error-Preprocess" step | Internal | Sanjit Mondal | Resolved | There is a failure in App03 in “Error-Preprocess” step. we proceed with the similar steps like we did previously- “For the current batch rejected the file from Error-Preprocess state”.So Rejected the failed file. And file send to R&D for investigation. Modified ftp script to implement error file checkong
App03 | 16.09.2025 |  | file failure in "error-pre-process" step | Failure in "Error-Preprocess" step |  |  | Resolved | There is a failure in App03 in “Error-Preprocess” step. we proceed with the similar steps like we did previously- “For the current batch rejected the file from Error-Preprocess state”.So Rejected the failed file. And file send to R&D for investigation. Modified ftp script to implement error file checkong
App02 | 16.09.2025 | Surya Kant Sharma | JobWorkflowCtrl" & " CM_Report_extract " jobs were in terminated state | Tsel App02- "JobWorkflowCtrl" & " CM_Report_extract " jobs were in terminated state du to Child job failed JobWorkflow | Internal |  | under investigation
App03 | 17.09.2025 |  | file failure in "error-pre-process" step | Failure in "Error-Preprocess" step |  |  | Resolved | There is a failure in App03 in “Error-Preprocess” step. we proceed with the similar steps like we did previously- “For the current batch rejected the file from Error-Preprocess state”.So Rejected the failed file. And file send to R&D for investigation. Modified ftp script to implement error file checkong
App02 | 20.09.2025 | Sakshi Sharma | JobWorkflowCtrl" & "InvLic_Report_extract" jobs got terminated | JobWorkflowCtrl" job got terminated due to child job failed also "InvLic_Report_extract" got terminated | Internal | Sakshi Sharma | Resolved | . We have had restart both the jobs and executed "InvLic_Report_extract". Post that Inventory report had been generated.
App01 | 21.09.2025 | Sakshi Sharma | Both(Inventory & OSS load) didn't initiate today | Today we observed that INV & OSS both loads didn’t initiate. As per the further investigation Jboss service was in running state and as per the server logs it seems that there is some connection issue | Internal | Mehul | Resolved | checked if VM got restarted or not. Also provided var logs to the Engg. Team
App02 | 23.09.2025 | Sakshi Sharma | JobWorkflowCtrl" & " CM_Report_extract " jobs were in terminated state | Tsel App02- "JobWorkflowCtrl" & " CM_Report_extract " jobs were in terminated state du to Child job failed JobWorkflow | Internal
App01 | 23.09.2025 | Sakshi Sharma | JobWorkflowCtrl" & "cleanworkschema" jobs got terminated | JobWorkflowCtrl" & "cleanworkschema" jobs got terminated | Internal | Sakshi Sharma | under investigation | Re-started both the jobs. Also, CM & INV report was not generated, so we manually executed both the jobs(CM_Report_extract and InvLic_Report_extract) post triggered these jobs reports was generated
App03 | 24.09.2025 | Anton Nugroho | Admin console inaccessible, JBOSS down, Inventory Data error-Import-CreateMetaData | Admin console inaccessible, JBOSS down, Inventory Data error-Import-CreateMetaData | Internal | Anton Nugroho | Resolved | 1. JBOSS down - we Start JBOSS, 2. Inventory error-Import-CreateMetaData - we proceed with Next. Email sent to customer and SML regarding the issue. modified JVM parameter to 20 gb as per R&D.
App02 | 25.09.2025 | Surya Kant Sharma | 1.Failed Inv feed in ‘Error-Import-Commit’ due to commit ReferenceError: "RunTav" is not defined., after few min. 2.‘JobWorkflowCtrl’ and ‘InvLic_Report_extract’ job was terminated due to Child job failed JobWorkflow. | 1.Failed Inv feed in ‘Error-Import-Commit’ due to commit ReferenceError: "RunTav" is not defined., after few min. 2. ‘JobWorkflowCtrl’ and ‘InvLic_Report_extract’ job was terminated due to Child job failed JobWorkflow. | Internal | Surya Kant Sharma | under investigation | 1. Failed Inv feed in ‘Error-Import-Commit’ - we proceed with Next. 2. Rerun both the jobs and executed "InvLic_Report_extract" job.
App02 | 27.09.2025 | Surya Kant Sharma | Failed Inv feed in ‘Error-Import-Commit’ | Failed Inv feed in ‘Error-Import-Commit’ due to commit ReferenceError: "enableNetworkStreamValidate" is not defined. | Internal | Surya Kant Sharma | Resolved | Failed Inv feed in ‘Error-Import-Commit’ - we proceed with Next. Suggested by Rohan : Due to connection sudden network connection issue between application and DB server it happens rarly.
App02 | 30.09.2025 | Sakshi Sharma | Migrate feed of INV Data is in "Error-Import-Commit" | migrate feed of INV Data Load is in “Error-Import-Commit” due to ORA error, some index is in unusable state. | Internal | Neena Ji | Resolved | Neena rebuild all unusable sub partition level indexes. It will take time. "Once the rebuild activity is completed, the feed needs to be Next with no other action."
App01 | 30.09.2025 | Sakshi Sharma | Tsel App01 - OSS data load is stuck in merge step | files received today were more in count for Huawei HAB (Autobak) and the Ericsson files were received less. Also did the FTP scripts pulled files late today since the files got processed later than other days. If that is the case then this first needs to be addressed. | Internal | Sakshi/Anton | Resolved | reject the currunt feed and One another load has been re-initiated.
App01 | 01.10.2025 | Sakshi Sharma | OSS & INV Data load did not move to Import feed | OSS & INV Data load did not move to Import feed after batch completed | Internal | Sakshi/Mehul | Resolved | After analysing we found that “jobworkflowctrl” job was terminated when the migrate feed of INV was about to move into Import, because of this feed did not move to Import. We triggered OSS migrate feed to import and could not trigger INV migrate feed because of time constraint
App02 | 01.10.2025 | Sakshi Sharma | Migrate feed of INV Data is in "Error-Import-Commit | 1. The Import-Commit workflow state is not in “Terminated” state. 2. The current sql run step (from the Admin console) is active in the DB also. View the Monitor Sessions of SQL Developer. 3. If there are any other active DB sessions. | Internal | Sakshi/Mehul | Resolved | 1. We have checked 1 query was stuck on Stream_entity table because “Gather stats” job was running when the INV feed was still running in step 89. 2. When we restart the process that stuck query got released and feed moved from step 89 to next step(120) in import-commit. 3. Currently, feed is moving and in Import-Audit step.
App03 | 01.10.2025 | Anton Nugroho | jboss service was down for few seconds | jboss service was down for few seconds | Internal | Anton Nugroho | Resolved | restarted the JBoss services.
App02 | 05.10.2025 | Surya Kant Sharma | Migrate feed of INV Data was in "Error-Import-Commit | We have found migrate feed of INV Data Load was in “Error-Import-Commit” due to commit ReferenceError: "RunTav" is not defined. | Internal | Surya Kant Sharma | Resolved | We have “NEXT” the feed and after 'next' the feed IL feed completed
Stg1 | 05.10.2025 | Surya Kant Sharma | Tsel Stg1: We have found OSS feed Data Load failed in “Failed Pre-GTB” | The issue is due to password expiry of scmgtb user..Tsel Stg1: We have found OSS feed Data Load failed in “Failed Pre-GTB” due to ‘update EUtranCellFDD null’. We have “NEXT” the feed but it is coming again in error. | Internal | Sanjit Mondal/Surya Kant Sharma | Resolved | The OSS batch load is rejected, Parser and loader output folder data is cleaned, Services are restarted and the OSS batch is re-initiated. After that feed again failed. So Engg team suggest for these action : Caused by: javax.resource.ResourceException: IJ000453: Unable to get managed connection for java:jboss/datasources/GtbDataSource Caused by: java.sql.SQLException: ORA-28001: the password has expired Kindly reset the password and back the feed once done (Refer to documentation if a new password string has to be configured). Also check if there are any other DB users with expired password or under grace. Additionally, please plan to include the password expiry in the checklist to avoid these kind of issues (DBA team can be consulted for SQL scripts)
Stg2 | 06.10.2025 | Surya Kant Sharma | Cause is found to be java.lang.OutOfMemoryError: GC overhead limit exceeded. Tsel Stg2 : 1 . we found issues like Cache Refresh did not run | Tsel Stg2 : 1 . we found issues like Cache Refresh did not run after complete the Oss feed. 2. Both ‘Oss & Inv’ Batch load completed. 3. Oss Feed ‘Import Complete’ done. 4. Inv feed ‘Import Complete not done. | Internal | Sanjit Mondal/Surya Kant Sharma | Resolved | suggested by Rohan: For a fix, we would need to have a change done in the –xmx property, to increase the memory limit. I would request you to have a look into the value of this property in Prod App01 server as a reference and change the value of this property in TSel-Stg2 to what it is in App01 to avoid this issue. We would also require a Service Restart after this activity is done. fix it by Sanjit Da : Previous JVM memory settings in STG2 was –Xmx6144M. We have modified it to -Xmx20480M as it is in App01 and also restarted the service. Now we will initiate a new set of feed and monitor the system
App02 | 08.10.2025 | Sakshi Sharma | "JobWorkflowCtrl" & "InvLic_Report_extract" got terminated | "JobWorkflowCtrl" & "InvLic_Report_extract" got terminated due to child job failed. | Internal |  | under investigation | restarted both the jobs and executed InvLic_Report_extract job manually.
Stg1 | 09.10.2025 | Sanjit Mondal | taking a long time to connect to the Tsel Staging-1 database through sqlplus | It is taking a long time to connect to the Tsel Staging-1 database through sqlplus, though all mount points have sufficient storage. | Internal | Sanjit Mondal/Neena ji | Resolved | mail sent to Neena (After few min Neena repleid that it is connected now)
Stg1 | 09.10.2025 | Surya Kant Sharma | We have found that GUI was not open due to managed connection issue | We have found that GUI was not open due to managed connection issue. Post restart the Jboss Oss data feed came into the ‘Error-Import-Diff’ due to ‘Non supported SQL92 token at position: 64’ We have “NEXT” the feed but it is coming again in error. | Internal |  | Resolved | Mail sent to R&D it was soposed to do clear 'Step' but after service restart it was showing clear 'State' so to revert that to the previous date we have perform following steps as per R&D guidelines. (SMARTCM 6335) . SELECT * FROM SQL_RUN WHERE SQL_RUN_ID IN (24094,24095,24096); UPDATE SQL_RUN SET LAST_UNFINISHED_FL=0,WAS_SUCCESSFUL=1 WHERE SQL_RUN_ID IN (24095,24096); UPDATE SQL_RUN SET LAST_UNFINISHED_FL=1,WAS_SUCCESSFUL=0 WHERE SQL_RUN_ID IN (24094); SELECT * FROM SQL_RUN_STEP WHERE SQL_RUN_ID=24094 ORDER BY 1; update sql_run_step set WAS_SUCCESSFUL=0,DATE_FINISHED=null,TABLE_REGISTRY_ID=null,status_msg=null where sql_run_id=24094 and SQL_RUN_STEP_ID=285007;
App04 | 10.10.2025 | Surya Kant Sharma | There is failure in ‘Erro-Import Commit’ | There is failure in ‘Erro-Import Commit’ due to ‘unique index SCMPROD.PK_STREAM_ENTITY_IX partition P_1_S_42404 initially in unusable state’. | Internal | Neena Ji | Resolved | According to Neena : Only 1 sub partition index was in unusable state now its in usable state. So we did go with 'next' from failed feed.
App02 | 12.10.2025 | Sakshi Sharma | "JobWorkflowCtrl" & "InvLic_Report_extract" got terminated | "JobWorkflowCtrl" & "InvLic_Report_extract" got terminated due to child job failed. | Internal | Mehul/Sanjit | under investigation | restarted both the jobs and executed InvLic_Report_extract job manually./ waiting for R&D to provide which DCC needs to be applied and when.
App03 | 15.10.2025 | Anton Nugroho | Jboss was down | Jboss was down due to VM was down | External | Anton Nugroho | Resolved | mail sent to SML. JVM Parameter changed to 20 gb as per R&D.
App02 | 17.10.2025 | Surya Kant Sharma | "JobWorkflowCtrl" & "InvLic_Report_extract" got terminated | JobWorkflowCtrl & "InvLic_Report_extract" got terminated due to child job failed. | Internal | Surya Kant Sharma | under investigation | restarted both the jobs and executed InvLic_Report_extract job manually.
App01 | 22.10.2025 | Sakshi Sharma | Migrate feed of Inv load got failed in “Import-ETL” step | Migrate feed of Inv load got failed in “Import-ETL” step due to ORA-01555 error. | Internal | Sakshi Sharma | Resolved | The feed has now moved past the step. One observation though, the Import-ETL step “collecting active attribute records for HUAWEI INVENTORY License510-254005” has started to take more time from last 2 days. Earlier the steps used to get complete in around 10 – 15 minutes and now it is more than an hour. Likewise the Inventory feed timing have increased from 1.5 hours to almost 4 hours.
App01 | 24.10.2025 | Sakshi Sharma | “jobwrkflowctrl”, “InvLic_report_extract” jobs got terminated | “jobwrkflowctrl”, “InvLic_report_extract” jobs got terminated | Internal | Sakshi Sharma | under investigation | “jobwrkflowctrl”, “InvLic_report_extract” jobs got terminated. We have restarted the jobs and manually triggered “InvLic_report_extract”.
App02 | 24.10.2025 | Sakshi Sharma | “jobwrkflowctrl”, “InvLic_report_extract” & “Import-hold” jobs got terminated | “jobwrkflowctrl”, “InvLic_report_extract” & “Import-hold” jobs got terminated | Internal | Sakshi Sharma | under investigation | We have restarted the jobs and manually triggered “InvLic_report_extract”. NOTE: We have applied DCC yesterday for this re-occurring issue in App02.
App03 | 28.10.2025 | Anton Nugroho | 1 file having error-preprocess | 1 file having error-preprocess | Internal | Anton Nugroho | Resolved | There is a failure in App03 in “Error-Preprocess” step. we proceed with the similar steps like we did previously- “For the current batch rejected the file from Error-Preprocess state”.So Rejected the failed file. And file send to R&D for investigation. We did not find any corrupted raw file for that day. The reported XML file(with invalid XML character (Unicode: 0x1f)) was prepared by the combiner. Header and footer was appended properly in the file. Means combiner completed his file combining process successfully. Still looking into the issue. ftp script changed for checking error file.
App01 | 28.10.2025 | Surya Kant Sharma | JobWorkflowCtrl & "InvLic_Report_extract" jobs are in terminated state due to child job failed | "JobWorkflowCtrl" & "InvLic_Report_extract" jobs are in terminated state due to child job failed | Internal | Surya Kant Sharma | under investigation | We have restarted both the jobs and they are in ready state now. And Inv report is yet to be generated so We have executed the “InvLic_Report_extract” job manually.
App03 | 30.10.2025 | Anton Nugroho | Admin console inaccessible - Jboss down, . Inventory error-Import-ETL | Admin console inaccessible - Jboss down, . Inventory error-Import-ETL | Internal | Anton Nugroho | Resolved | Started JBOSS, and Inventory error-Import-ETL - proceeded with Next. We analyzed the server logs and found no logging between 5.50 AM – 6.38 AM i.e., till the service was started. The service went down abruptly during this period. JVM modified to 20gb as per R&D.
App02 | 30.10.2025 | Surya Kant Sharma | JobWorkflowCtrl & "Laccima_Report_extract" jobs are in terminated state due to child job failed | "JobWorkflowCtrl" & "Laccima_Report_extract" jobs are in terminated state due to child job failed | Internal | Surya Kant Sharma | under investigation | We have restarted both the jobs and they are in ready state now. And Inv report is yet to be generated so We have executed the “Laccima_Report_extract” job manually.
App01 | 31.10.2025 | Shaikh Imtiar Rahaman | "JobWorkflowCtrl" & " CM_Report_extract" jobs got into terminated state due to child job failure | "JobWorkflowCtrl" & " CM_Report_extract" jobs got into terminated state due to child job failure | Internal | Shaikh Imtiar Rahaman | under investigation | Step 1 - Select "JobWorkflowCtrl" and Restart the job. Step 2 - Select "CM_Report_extract" and Restart the job. Step 3 - Select "CM_Report_extract" and Execute the Job
App02 | 01.11.2025 | Shaikh Imtiar Rahaman | Inventory feed failure in Import-BusinessRules | Inventory feed failure in Import-BusinessRules | Internal | Shaikh Imtiar Rahaman | under investigation | Step 1 - Select the feed which was in Error-Import-BusinessRules. Step 2 - In the above dropdown, click on "Next" and then click on "Apply" to move the feed. No repply from R&D yet.
App02 | 02.11.2025 | Shaikh Imtiar Rahaman | "Report-Notify" job was down | "Report-Notify" job was down | Internal | Shaikh Imtiar Rahaman | Resolved | Restarted the "Report-Notify" job manually
App03 | 05.11.2025 | Shaikh Imtiar Rahaman | "JobWorkflowCtrl" & " CM_Report_extract" jobs got into terminated state due to child job failure | "JobWorkflowCtrl" & " CM_Report_extract" jobs got into terminated state due to child job failure | Internal | Shaikh Imtiar Rahaman | under investigation | Step 1 - Select "JobWorkflowCtrl" and Restart the job. Step 2 - Select "CM_Report_extract" and Restart the job. Step 3 - Select "CM_Report_extract" and Execute the Job
Staging 1 | 05.11.2025 | Shaikh Imtiar Rahaman | "CreateBatch" job got terminated | "CreateBatch" job got terminated | Internal | Shaikh Imtiar Rahaman | Resolved | Step 1 - Select the "CreateBatch" job and restart the job manually
App01 | 07.11.2025 | Shaikh Imtiar Rahaman | "CreateBatch" job got terminated | "CreateBatch" job got terminated | Internal | Shaikh Imtiar Rahaman | under investigation | Step 1 - Select "CreateBatch" job and restart the job manually. as per R&D on 11th Nov. mail it is referring it is indicating a double trigger of the process somehow, which could have caused the automatic failure in the first instance. Repplied on 7th november they will further investigate on it.
App02 | 11.11.2025 | Shaikh Imtiar Rahaman | Inventory feed failure in Error-Import-Commit due to commit ReferenceError: "enableNetworkStreamValidate" is not defined. | Inventory feed failure in Error-Import-Commit due to commit ReferenceError: "enableNetworkStreamValidate" is not defined. | Internal | Shaikh Imtiar Rahaman | under investigation | Mannual Steps Taken - Step 1 - Select the Inventory feed in Error-Import-Commit. Step 2 - Select "Next" and click on "Apply". ------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------ Message from R&D - The Import-Commit state failed due to below error: java.nio.channels.ClosedChannelException The possible cause of the above exception could be a Network Disconnect. Also there seems to be a dbping.sh (/opt/teoco/smartcm/dbping.sh) script running every minute. Is it something that we have enabled. Please share the script in txt format. ------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------- ( The Script "dbping.txt" and the output "tnspingresult.txt" is shared with R&D. Waiting for their reply)
App02 | 11.11.2025 | Shaikh Imtiar Rahaman | "JobWorkflowCtrl" and "InvLic_Report_extract" jobs got into terminated state due to child job failure | "JobWorkflowCtrl" and "InvLic_Report_extract" jobs got into terminated state due to child job failure | Internal | Shaikh Imtiar Rahaman | under investigation | Step 1 - Select "JobWorkflowCtrl" and Restart the job. Step 2 - Select "InvLic_Report_extract" and Restart the job. Step 3 - Select "InvLic_Report_extract" and Execute the Job
App01 | 11.11.2025 | Chayanika Porel | WIB 2025 : pv-icamtbs1-app16-01 is Running out of space on disk mount point --> /u01 utilization reached 91% | WIB 2025 : pv-icamtbs1-app16-01 is Running out of space on disk mount point --> /u01 utilization reached 91% | Internal | Chayanika Porel | Resolved | Have added 6 new directories from DataReplication ,extInvREPORT,extCMREPORT,extREPORT,tmp/h13,logs in the diskcleanup script. It will remove files which are 1 - 1.5 months old
App02 | 11.11.2025 | Chayanika Porel | Preventive measure and synchronization as App01 | N/A | Internal | Chayanika Porel | In Progress
App03 | 11.11.2025 | Chayanika Porel | Preventive measure and synchronization as App01 | N/A | Internal | Shaikh Imtiar Rahaman | In Progress
App04 | 11.11.2025 | Chayanika Porel | Preventive measure and synchronization as App01 | N/A | Internal | Shaikh Imtiar Rahaman | In Progress
App01 | 12.11.2025 | Shaikh Imtiar Rahaman | OSS feed failure in Import-Commit in App01 | OSS feed failure in Import-Commit in App01 | Internal | Shaikh Imtiar Rahaman | Resolved | Please refer to the DCC Jira-SMARTCM-6975, for the resolution of the issue below. Listing the steps to be followed for the resolution here: 1.) Run the attached script “dedup_avm.xml” using the Auto-installer following the below steps: a.) Copy the attached file on to the server. b.) Navigate to ~SmartCM/scripts c.) Execute the below command: ./installer.sh <absolute-path>/dedup_avm.xml -6975 2.) Validate the effectiveness of the DCC by running the Query as part of the text file, “DCC6975_Validation_query.txt”, manually from the SQL Developer. This query should not return any row. 3.) In case of the success of the above 2 steps, Perform a “Next” in the feed.
App03 | 13.11.2025 | Shaikh Imtiar Rahaman | Inventory feed failure in Import-Commit in App03 | Inventory feed failure in Import-Commit in App03 | Internal | Shaikh Imtiar Rahaman | under investigation | Step 1 - Select the Inventory feed in Error-Import-Commit. Step 2 - Select "Next" and click on "Apply". ( Mailed R&D regarding the issue with server log. Waiting for their reply)

## DCC Implementation
Servers | Date of Implementation | DCC Name | Purpose/Issue
App01 | 2025-03-11 | SMARTCM-6975 | 1. The error is caused while trying to insert data into ATTRIBUTE_VALUE_MAP table. 2. The table maintains the mapping between Vendor and User value. 3. However per the Vendor Documentation two vendor values are mapping to same User value. This in turn causes the statement to fail.
All Prod Servers | 2025-04-11 | SMARTCM-7133 | DCC has been raised to enable logging at DEBUG level for Inventory and CM report extract jobs.
All Prod Servers + Staging1 | 2025-04-18 | SMARTCM-7160 | DCC has been applied because Group icon not visible
App03 | 2025-04-28 | SMARTCM-7120 | DCC has been applied in App03 to resolve invalid XML file issue
Staging1 | 2025-05-30 | SMARTCM-7212 & SMARTCM-7194 | SMARTCM-7194 : Alter the rule so batch will not wait in Hold state if a feed for other dataset is in progress. SMARTCM-7212 : Optimization of SONAR tables update procedure.
Staging1 | 2025-07-02 | SMARTCM-7244 | This DCC will resolve the external API performance issues related to accessing SRAN Network Tree data.It will update entries in the cache table, ensuring that external API queries are automatically cached after each load.
Staging1 & App04 | 2025-07-09 | SMARTCM-7250 | Database Access for Third Parties
Staging+App02/03/04 | 2025-08-05 | SMARTCM-7160 | Group icon not visible in production after V9 Upgrade
App01 | 2025-08-10 | SMARTCM-7160 | Group icon not visible in production after V9 Upgrade
Staging1 | 2025-08-18 | SMARTCM-7290 | for deployment in the TSEL-Stg environment
Staging1 | 2025-08-22 | SMARTCM-7223 & SMARTCM-7284 | SMARTCM-7223 : Optimization of License BSC Report SMARTCM-7284 : Optimization of License Consumption report
Staging1 | 2025-08-29 | SMARTCM-7302 | SMARTCM-7302 for QA
Staging2 | 2025-09-01 | SMARTCM-7194, SMARTCM-7212, SMARTCM-7223, SMARTCM-7284, SMARTCM-7160 & SMARTCM-7290 | SMARTCM-7194 : Refinement of batch Hold rule. SMARTCM-7212 : Optimize the procedure sp_set_batch_row_load_count. SMARTCM-7223 : Optimization of License BSC Report. SMARTCM-7284 : Optimization of License Consumption report. SMARTCM-7160 : group icon. SMARTCM-7290 : API
App02 | 2025-10-22 | SMARTCM-7370 | Deployment of Optimized Antenna_Port_Usage
App02 | 2025-10-27 | SMARTCM-7370 | again DCC SMARTCM-7370 has been deployed in App02. Flush Query Cache and Sync is also done
Stg1,Stg2 | 11.11.2025 | SMARTCM-7303 | has been implemented in both STG1 & STG2
App01 | 12.11.2025 | DCC SMARTCM-6975 | 1. The error is caused while trying to insert data into ATTRIBUTE_VALUE_MAP table. 2. The table maintains the mapping between Vendor and User value. 3. However per the Vendor Documentation two vendor values are mapping to same User value. This in turn causes the statement to fail.